| COVER, REVISION HISTORY AND APPROVAL PAGE |  |  |
| --- | --- | --- |
| Revision No. | Brief Description of Change | Effectivity Date |
| 0 | Origination |  |

|  | Name | Signature |
| --- | --- | --- |
| Originated/ Revised by: | Virtron K. Bumal-o Project Manager | See DCN |

| Reviewed by: | Sherman A. Semanero Project Manager | See DCN |
| --- | --- | --- |
|  | Marjorie Laranang Olivete Admin Director/ QMR | See DCN |

| Approved by: | Fernando C. Laranang President/CEO | See DCN |
| --- | --- | --- |
| Date Approved |  |  |

Distribution List

| President/CEO | Project Manager’s (2) | Document Controller |  |
| --- | --- | --- | --- |
| QMR/BOD’s | Admin (Common Copy) |  |  |

- PURPOSE AND SCOPE

To establish a structured and transparent process for selecting the most suitable contractor for a construction project, ensuring fairness, compliance with regulations, and achieving the best value for the project owner.

This procedure applies to all construction projects undertaken by FCLDC, from small-scale renovations to large-scale developments. It includes all steps from project announcement to post-award activities.

- REFERENCE DOCUMENTS

FCLDC QAQC Manual

Plans and Specifications

Contract Documents

- DEFINITIONS

3.1	Definitions

Service agreement – Contract Between the General contractor stating the date the sub-contractor can begin work subject to the conditions stated on the agreement.

Plans and Specifications - a key part of the process of constructing a project. These documents are means of communicating between parties, and of ensuring that the appropriate designs, materials and construction techniques are used.

Bid - A proposal submitted by a contractor in response to the bid documents.

Bid Documents - The collection of documents provided to contractors, including project specifications, drawings, and contract terms.

Prequalification - The process of evaluating and shortlisting contractors based on specific criteria before inviting them to submit bids.

Evaluation Committee - A group of experts assembled to review and assess the submitted bids.

Letter of Intent - A document issued to the selected contractor indicating the intent to award the contract, subject to final negotiations.

Kick-Off Meeting - An initial meeting held with the selected contractor to review project details and establish communication channels.

- GENERAL REQUIREMENTS

4.1 Equipment, Materials and Documents

    - Licenses and Certifications - Contractors must hold all necessary licenses and certifications to perform the work. (PCAB license/ Business permit)

    - Compliance with Laws and Regulations - Contractors must comply with all applicable laws, regulations, and industry standards.

    - Insurance and Bonding - Contractors must provide proof of adequate insurance coverage and bonding as required by FCLDC.

    - Experience and References - Contractors must demonstrate relevant experience and provide references from similar projects.

    - Financial Stability - Contractors must provide evidence of financial stability, such as financial statements or credit reports.

    - Subcontractor Management - Contractors must have a plan for managing subcontractors, including vetting and coordinating their work.

    - Project Schedule - Contractors must submit a detailed project schedule, including key milestones and deadlines.

  - Safety and Environmental

    - Each worksite and employee function are thoroughly assessed in a manner that ensures safety for themselves, property owners and representatives, the general public, and the environment.

    - Safety Records: Contractors must provide their safety records and demonstrate a commitment to maintaining a safe work environment.

- PROCEDURE / INSTRUCTIONS

# Procedure Outline

5.1	Project Announcement

5.2	Prequalification of Contractors

5.3	Issuance of Bid Documents

5.4	Pre-Bid Meeting

5.5	Bid Submission

5.6	Bid Evaluation

5.7	Contract Award

5.8	Post Award Activities

# Procedure Details

| Responsible Person | Activities | Interface Document/Person |
| --- | --- | --- |
|  | 5.1 Project Announcement |  |
| Finance Project Mananger | - Prepare Project Description - Create a comprehensive project brief detailing the scope, objectives, timeline, budget, and specific requirements. | Gencon and sub-con |
| QA/QC Engineer | - Publish the project announcement on industry | Contractor |
|  | - Prequalification of Contractors |  |
| Technical Team | - Send out a questionnaire requesting information on financial stability, past project experience, technical expertise, safety records, and other relevant criteria. - Review the submitted questionnaires and assess each contractor’s qualifications. Create a shortlist of contractors who meet the criteria. | Sub-contractor |
|  | 5.3 Issuance of Bid Documents |  |
| Technical Team | - Compile all necessary documents, including project specifications, architectural and engineering drawings, contract terms, and conditions. - Send the bid documents to the prequalified contractors, ensuring they have sufficient time to review and prepare their bids. | Bar Chart/S-Curve |
|  | 5.4 Pre-Bid Meeting |  |
|  | 5.4.1 Schedule Pre-Bid Meeting - Organize a meeting with all shortlisted contractors to discuss the project in detail. 5.4.2 Discuss Project Scope and Requirements - Go over the project scope, timelines, technical requirements, and expectations. - Address any questions or concerns raised by the contractors to ensure everyone has a clear understanding of the project. |  |
|  | 5.5 Bid Submission |  |
|  | - Set Deadline for Bid Submission: Establish a clear deadline for when bids must be submitted. - Provide Submission Instructions: Offer detailed instructions on the format, required documents, and method of submission. - Collect and Record Bids: Receive and record all submitted bids, ensuring they are kept confidential until the evaluation phase. |  |
|  | 5.5 Bid Evaluation |  |
|  | - Form Evaluation Committee: Assemble a team of experts to review and evaluate the bids based on pre-defined criteria. - Assess Bids: Evaluate bids considering factors such as cost, proposed schedule, technical approach, contractor’s experience, and past performance. - Conduct Interviews (if necessary): If needed, hold follow-up meetings or interviews with the top bidders to gain further insights into their proposals. |  |
|  | 5.6 Contract Award Contract Award Objective: Select and notify the winning contractor. Steps: Evaluate Final Bids: Conduct a thorough review of the final bids and select the contractor that offers the best value and meets project requirements. Notify Selected Contractor: Inform the winning contractor and issue a letter of intent. Negotiate and Finalize Contract: Discuss and agree upon the final contract terms with the selected contractor. Formal Award of Contract: Formally award the contract to the winning contractor and obtain necessary signatures. Post-Award Activities Objective: Ensure a smooth project start and establish communication channels. Steps: Conduct Kick-Off Meeting: Organize a meeting with the selected contractor to review project details, establish timelines, and assign responsibilities. Review Project Schedule and Responsibilities: Go over the project schedule, key milestones, and roles of all parties involved. Establish Communication Channels: Set up regular communication and reporting procedures to ensure effective coordination and address any issues promptly. |  |

# 7.0	APPENDICES

# Service Agreement

# PM-OPN-02-14Masonry Checklist form

# Billing form