| COVER, REVISION HISTORY AND APPROVAL PAGE |  |  |
| --- | --- | --- |
| Revision No. | Brief Description of Change | Effectivity Date |
| 0 | Origination | April 23, 2019 |
| 1 | Procedure on Corrective action report and Coordination meeting included. Document code on corresponding forms also included in the interface column | October 24, 2023 |
| 2 | Roles and responsibilities of QCE and QS included in the procedure, definitions of project engineering and technical team included, innterface document on the right column was revise from FCLDC-SPQAQC to FCLDC -QAQC Manual, forms also included in the interface column | October 24, 2024 |

|  | Name | Signature |
| --- | --- | --- |
| Originated/ Revised by: | Engr. Virtron Bumal-o/ Marjorie L. OLivete Operations Manager / QMR | See DCN |

| Reviewed by: | Sherman A. Semanero Operations Manager | See DCN |
| --- | --- | --- |
|  | Richelle D. Eslava HR Manager/Deputy QMR | See DCN |

| Approved by: | Marjorie L. Olivete Admin Director / QMR | See DCN |
| --- | --- | --- |
| Date Approved | October 24, 2023 |  |

Distribution List

| President/CEO | Operation Manager’s (2) | Project Manager’s (5) |  |
| --- | --- | --- | --- |
| QMR/BOD’s | Admin (Common Copy) | Document Controller |  |

- PURPOSE AND SCOPE

To establish procedures in implementing various operations through proper coordination and control of planning and construction execution in the entire process.

- REFERENCE DOCUMENTS

FCLDC Comprehensive Quality Assurance and Quality Control Program (CQAQCP)

Plans and Specifications

Contract Documents

- DEFINITIONS

3.1	Definitions

Notice to Proceed – Letter from a principal (client or owner) to a contractor stating the           date the contractor can begin work subject to the conditions of the contract. The performance time of the contract starts from the NTP date.

Project Owner- is an entity that initiates project, finance it, contract it out and benefits from its output. Also called the owner.

Contract Documents – a formal agreement between an owner and a building contractor. Setting forth the terms under which construction is to be carried out, time scale, and penalties if any for failure to comply with terms of the contract.

Mother Schedule – outlines the typical time frame of work. This graph highlights the key stages in the project, along with recommended starting points for specific tasks. These are the consolidated schedule of Civil, Architectural and MEPF works.

Plans and Specifications - a key part of the process of constructing a project. These documents are means of communicating between parties, and of ensuring that the appropriate designs, materials and construction techniques are used.

Temfacil – the temporary facilities need by Project team established at the customer premises

Construction Methodologies – Outline the philosophies underlying the staging and sequencing options selected in construction. Highlights key features of operations for a specific task.

Project Management- is the practice of initiating, planning, executing, controlling, and closing the work of a team to achieve specific goals and meet specific success criteria at the specified time.

Project Engineering and Technical Team - a group of professionals assembled for the execution of a particular project, with each member having a unique skill set vital for the successful completion of the project (PM’s, QS, QCE, Safety Officers, Site engineers etc.)

Bar Chart/S-Curve – a diagram showing the series of activities against time lines until completion of the scope of works

FCLDC-Specific Project Quality Management Plan (FCLDC-SPQMP) – a document that details the description of quality control systems that include staff roles and relationship, procedures and any other resources that relate to producing high quality work output.

Purchasing and Logistic Officer- the department responsible for the purchasing of materials and equipment needed for the project.

Test Certificate – a document showing that the material used or installed in the project passed the minimum requirement specified in the plans and specifications.

- GENERAL REQUIREMENTS

4.1 Equipment and Materials

    - Contract Documents, plans and specifications

    - Permits and licenses (LGU, DOLE, DENR, Barangay Permits, etc.)

    - Project Organizational Chart

    - Computers and office supplies

  - Safety and Environmental

    - Each worksite and employee function are thoroughly assessed in a manner that ensures safety for themselves, property owners and representatives, the general public, and the environment.

- PROCEDURE / INSTRUCTIONS

# Procedure Outline

5.1	Issuance of Notice to Proceed by Client

5.2	Mobilization and installation of temporary facilities and Safety requirements

5.3	Project scheduling and Material take-off

5.4	Methodologies

5.5	Execution and Monitoring

5.6	Project Reporting

# Procedure Details

| Responsible Person | Activities | Interface Document/Person |
| --- | --- | --- |
|  | 5.1 Issuance of Notice to Proceed (NTP) |  |
| Owner and/or Management/ Consultant | - Client or Owner issues written notice to the contractor when the project will formally start. The performance time of the contract starts from the NTP date. Note: The official day one of the project depends on the conditions set forth in the contract agreement. | Contractor NTP |
|  | - Mobilization and installation of temporary facilities (Temfacil) |  |
| Project Engineering and Technical Team | - Conduct site inspection to verify the actual site condition in relation to the master plan. It includes performing lot survey and topographic mapping. | Project Owner and/or Project Management/ Consultant, FCLDC- QAQC Manual Site Inspection Checklist (FM-OPN-02-02) |
| Project Engineering and Technical Team | - Develop a site plan showing the locations and dimensions of temporary facilities (including layouts and details, equipment and material storage area (onsite and offsite), and access and haul routes, avenues of ingress/egress to the fenced area and details of the fence installation. | FCLDC- QAQC Manual FCLDC- SAFETY Manual |
| Project Engineering and Technical Team | - Identify any areas which may have to be graveled to prevent the tracking of mud. Indicate if the use of a supplemental or other staging area is desired. | FCLDC- QAQC Manual FCLDC- SAFETY Manual |
| Project Engineering and Technical Team | - Establish locations of safety and construction fences, site trailers, construction entrances, trash dumpsters, temporary sanitary facilities, and parking areas, etc. | FCLDC- QAQC Manual FCLDC- SAFETY Manual |
| Project Engineer | - Mobilization of physical and manpower resources to the construction site. | Motor pool Supervisor |
|  | 5.3 Project Scheduling and Material take-off |  |
| Project Manager | - Prepare the Mother Schedule based on the project duration stated in the contract. | Bar Chart/S-Curve |
| Project Manager Quantity Surveyor | - Determine the number and type of workers that will be needed for the project and issue manpower schedule to HR for hiring. The manpower schedule shall be submitted to HR department at least one week before mobilization. | HR Manager Manpower Schedule |
| Operation Mgr. Project Manager Quantity Surveyor QC Engineer | PM to submit to purchasing and logistic department a list of major materials needed one month prior to date of installation. The goal is to have the materials available when necessary. They should not arrive too early and certainly should not arrive late. Roles and responsibilities: QCE to verify that the delivered materials comply with the specifications outlined in the contract. Refer to FCLDC QAQC manual - inspection and test plan QS to monitor estimated quantity vs actual quantity installed. Responsible for performing the material takeoff by providing detailed and accurate material estimates that inform the project cost estimates and budget. OM’s and PMs oversee the process and ensure that the material takeoff aligns with the project’s scope, timelines and budget. They help prioritize the materials based on project phases. Site engineers to review the technical drawings to ensure that the materials meet structural and engineering specifications, are suitable for the integrity and performance of the project and are technically accurate. | Purchasing and Logistics Material take-off schedule (FM-OPN-02-23) Project Cost Estimate Material specifications FCLDC- QAQC Manual |
|  | 5.4 Methodologies |  |
| Project Engineering and Technical Team | - Determine critical areas that needs to be addressed during implementation. The team will come-up with methodologies as guidelines in ensuring that work confirms to environment and safety standards and that the flow of work is in sequence and coordinated with the LGU concerned. | FCLDC- QAQC Manual FCLDC- SAFETY Manual Plans and Specifications Barangay Community |
|  | 5.5 Execution and Monitoring |  |
| Project Engineering and Technical Team | - Orientation of safety programs, company policies and QAQC procedures must be discussed to the workers before execution of the project or specific construction activities. - All QAQC control process for specific item of work must be conferred to all the employees and workers involve in such activities. - In the construction phase, the Engineering Team will execute the construction according to plans and specifications. Listed below are the guidelines to be implemented during this phase: *** Document controller to be given a soft copy of the construction plan/specifications as part of record keeping | Consultant/Project Management FCLDC- QAQC Manual Master list of Quality Records (FM-RNI-02-01) Document controller |
| Project Engineering and Technical Team | - Oversee the work performed by admin and sub-contractors, document these activities in accordance with the FCLDC procedures manual and QAQC manual. Refer all construction activities to the QAQC procedures outlined in the FCLDC-QAQC manual. Perform quality control as per QAQC requirements and instructions from the QCE. **Ensure that all approved plans and specifications should have “approved for construction stamp” | Plans and Specifications FCLDC- QAQC Manual |
| Project Engineering and Technical Team | - Ensure that quality assurance and quality control activities are in accordance with FCLDC-CQAQC program, unless otherwise specified on the general or technical specifications required by the client. - QCE to conduct audits of construction activites and workmanship quality on a weekly basis and to submit QAQC report to the CEO for information. - All non-conformities of standards/ specifications or customer complaints shall be documented and recorded thru the Non-conformance report or Corrective Action Report. Closure and/or monitoring of effectiveness of actions taken shall conform with Control of Non-conforming Products and Services Procedure | FCLDC- QAQC Manual Inspection Test Plan Non conformance report FM-OPN-02-24 Corrective action Report (FM-RNI-06-01) Control of Non-conforming Products and Services Procedure |
| Project Engineering and Technical Team | - Conduct internal weekly coordination meeting to discuss quality issues, Non conformance reports, corrective actions, schedule updates and other relevant issues affecting the progress of the project. Meetings together with the Owner, Project Management and/or interested parties shall also be documented. | Construction Meeting Minutes (FM-OPN-02-03) |
| Project Engineering and Technical Team | - Consolidate all documents, including progress chart, testing certificates, commissioning and accomplishment data’s to be compiled as project billing to be submitted in accordance to project contract and service agreement for sub-contractor billing | Progress Billing Procedure Sub-contractor Billing Procedure |
| Project Engineering and Technical Team | - Coordinate with the Project Management and Designers for additional details of plans, revisions or corrections in drawings and proposals initiated by the owner or contractor. Document all these activities and compile it for record purposes. ***Document Control to be given a copy of revisions/corrections in drawings and proposals initiated by the owner/contractor | Request for Approval (FM-OPN-02-20) Request for Information(FM-OPN-02-20) Master list of Quality Records (FM-RNI-02-01) Document controller |
| Project Engineering and Technical Team | - Document punch lists identified by the Project Management/Consultant or the Owner. Set schedule for rectification works, monitor and document status until acceptance by Owner is achieved. | Project Turn-over Procedure |
| Project Engineering and Technical Team | - All Forms generated from all procedures will be registered in the Master Lists of Forms for control and tracking of revisions. Compiled records, documents (internal and external) and forms shall have a summary listing located in every front page of compiled records or sample documents for easier accessibility. - Ensure that all external documents are validated through stamp mark/signature of the client or its representative indicating that the document is approved for construction/implementation | Masterlist of Internal Documents (ML-RNI-01) Masterlist of External Documents (ML-RNI-02 |
|  | 5.6 Project Reporting |  |
| Project Manager/Project Superintendent | - Operations Managers to submit Daily Accomplishment Report addressed to the CEO - Operations Managers to Submit weekly report with updated Bar Chart – S-Curve to the CEO thru email (electronic copy only) | CEO Daily Data & Narrative Report (FM-OPN-02-27) |
| QC Engineer | - QC Manager to submit QAQC weekly report on Major projects addressed to the OM and CEO |  |

# 7.0	APPENDICES

- FM-OPN-02-01	Pouring Request Form

- FM-OPN-02-02  	Site Inspection Checklist

- FM-OPN-02-03	Construction Meeting Minutes

- FM-OPN-02-04	Requests for Approval

- FM-OPN-02-05	Requests for Information

- FM-OPN-02-06   Records Masterlist

- FM-OPN-02-07	Testing Log

- FM-OPN-02-08	Premobilization Checklist

- FM-OPN-02-09	Quality Inspection Report

- FM-OPN-02-10	Work Completion List

- FM-OPN-02-11	Concrete Works Checklist

- FM-OPN-02-12	Rebar Works Checklist

- FM-OPN-02-13	Formworks Checklist

- FM-OPN-02-14	Masonry Works Checklist

- FM-OPN-02-15	Tile Works Checklists

- FM-OPN-02-16	Painting Works Checklist

- FM-OPN-02-17	Pouring Request Log Sheet

- FM-OPN-02-18	Revision Register

- FM-OPN-02-19	Concrete cylinder test summary register

- FM-OPN-02-20	RFA Tracking Log Sheet

- FM-OPN-02-20	RFI Tracking Log Sheet

- FM-0PN-02-22	Material Take-off Log Sheet ( to be deleted)

- FM-OPN-02-23	Material Take-off Schedule

- FM-OPN-02-24	Non-Conformance Report

- FM-OPN-02-25	Work Request (to be deleted)

- FM-OPN-02-26	Corrective Action Request (retain)

- FM-OPN-02-27	Daily Data & Narrative Report

- FM-OPN-02-28	Manpower Schedule (Structural)

- FM-OPN-02-29	Pressure Test Report

- FM-OPN-02-30	Hauling Form

- FM-OPN-02-31	Project Monitoring Report

- FM-OPN-02-32	Megger/ Insulation Test Report

- FM-RNI-06-01     Corrective Action Report

- FM-OPN-02-33	Excavation Checklist

- FM-OPN-02-34	Permit Update Template

- FM-OPN-02-35	Percentage Summary of Rebar Order