|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 2 |
|  |  | Eff. Date : |
|  |  | Page : 1 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

| COVER, REVISION HISTORY AND APPROVAL PAGE |  |  |
| --- | --- | --- |
| Revision No. | Brief Description of Change | Effectivity Date |
| 0 | Origination | February 19, 2019 |
| 1 | Procedure name-change from subcontractor billing to subcontractor monitoring. Added to procedure: subcontractor procurement, service agreement and evaluation procedure, Sub- contractor Request Form |  |

|  | Name | Signature |
| --- | --- | --- |
| Originated/Revised by: | Engr. Michael D. Corpuz Project Manager | See DCN |

| Reviewed by: | Engr. Virtron K. Bumal-o QA/QC Manager | See DCN |
| --- | --- | --- |
|  | Engr. Sherman A. Semanero QSM | See DCN |
|  | Katherine Tolentino Senior PLO | See DCN |
|  | Michael Rey Zordilla Finance Manager | See DCN |
|  | Lorraine Ashley Laranang-Josue Finance Director | See DCN |
|  | Marjorie L. Olivete Admin Director/ QMR | See DCN |

| Approved by: | Jan Ross Kyle Laranang Facilities Director | See DCN |
| --- | --- | --- |
| Date Approved |  |  |

Distribution List

| President / CEO | QA/QC Manager & QS Manager | Project Managers |
| --- | --- | --- |
| BOD’s | Operations Manager | Doc. Con / Admin (Common Copy) |

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 2 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

1.0   PURPOSE AND SCOPE

To provide guidelines and specify the needed requirements for the processing of subcontractor progress billing.

2.0   REFERENCE DOCUMENTS

Service Agreement

Project Plans and Specifications

Project Cost Estimate

Project Planning and Execution Procedure

3.0   DEFINITIONS AND ABBREVIATIONS

3.1 Definitions

General Contractor – is responsible for the day-to-day management of a construction site and the communication of information to all involved parties throughout the course of the building project. Their responsibility is to ensure that the project is completed according to the client’s specifications and in compliance with the existing laws.

Subcontractor – is a person or company hired by a general contractor to perform a specific task as part of the overall project and is normally paid for services provided to the project by the general contractor.

Service Agreement – is an agreement between two persons or businesses where one agrees to provide a specified service to the other including the terms of payment.

Subcontractor Billing – is an invoice that is intended to obtain payment from the General Contractor for that portion of project. The timeline and frequency of billing depends on the conditions set forth in the service agreement.

Working Drawings – these are illustrational drawings with the purpose of outlining the current and/or progress billing. These include detailed sketch of the scope of work to be billed either for data gathering or supplemental attachments.

Accomplishment Pictures – is a sequential presentation of documented pictures highlighting the progress of a specific work.

Accredited Subcontractor – is a subcontractor accredited by PLO department.

Provisionary Accredited Subcontractor – is a subcontractor not accredited by the PLO department due to noncompliance with the financial document requirements but can-do subcontracting works. Usually, these are subcontractors that has manpower resources only.

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 3 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

Cost Proposal - an itemized unit cost breakdown representing the cost of service/work to be rendered by the subcontractor. It is usually composed of a cover page letter, estimate, plans and specifications. This proposal is usually presented by a Specialty Work Subcontractor.

Quotation – is a simple cover page letter indicating the intent of the subcontractor to render service/work at a certain unit cost per unit of work (unit of work is hourly, sq.m., cu.m., etc.). This proposal is usually presented by Labor Only Subcontractors or Soil Haulers.

Labor Only Subcontractors – is a subcontractor who renders labor cost only services.

Specialty Contractors – is a subcontractor who supply materials and renders labor service at the same time.

3.2 Abbreviations

CEO          -         Chief Executive Officer

PM            -         Project Manager

PE            -         Project Engineer

PLO          -         Purchasing and Logistic Officer

QSM            -       Quantity Surveyor Manager

QSG           -        Quantity Surveyor Group

QA/QC       -         Quality Assurance/ Quality Control

4.0 GENERAL REQUIREMENTS

4.1 Equipment and Materials

•   Computer

•   Printer

•   Measuring Tools

•   Camera

•   Office supplies

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 4 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

5.0   PROCEDURE & INSTRUCTIONS

Procedure Outline

|  | 5.1. Subcontractor Procurement |  |
| --- | --- | --- |
|  | 5.2. Service Agreement |  |
|  | 5.3. Subcontractor Billing |  |
| 5.3.1. Validation 5.3.2. Assessment 5.3.3. Documentation |  |  |

5.3.4. Submission

5.4. Evaluation and Acceptance

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 5 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

Procedure Details

| Responsible Person | Activities | Interface Document/Person |
| --- | --- | --- |
|  | 5.1 Subcontractor Procurement |  |
| Operations Manager, Quantity Surveyor Group | • The Operations Manager shall request Accredited Subcontractors or Provisionary Accredited Subcontractors to the PLO Department. The Subcontractor shall submit a Quotation or Cost Proposal for the scope of the work being offered which will be assessed by the Operations Manager and the Quantity Surveyor group led by the Quantity Surveyor Manager. Assessment is being done to ensure that the subcontractor’s cost proposal will not overshoot the corresponding estimated cost or the budget that is allotted to the specific job offer. It is the task of the Quantity Surveyor Manager to negotiate with the potential subcontractor to obtain the best prices and terms for the job. Timeline of request prior to commencement of work shall be as follows: a. Labor Cost Only Subcontractors such as masonry, painting, tile works and other similar scope of works – 7 days. b. Soil Haulers – 14 days c. Specialty Works such as Slope Protection, STP provider, Solar System Installer, etc. – 30 days Note: Timeline includes negotiation of cost, drafting of service agreement and submission of required documents needed by PLO department and/or LGU clearances or requirements. | PLO, Subcontractor |
|  | 5.2 Service Agreement |  |
| PLO | • Upon approval of quotation of the subcontractor, the PLO department shall draft the service agreement in coordination with the Operations Manager and the Quantity Surveyor Manager. The Operations Manager and the Quantity Surveyor Manager shall have inputs on the cost/unit cost, timeline of service and Standard Operating Procedures (if required). The PLO department will be in-charge with the downpayment terms, progress billing, amount-period of retention and other legal provisions necessary for the Agreement. | Service Agreement, Operations Manager, Quantity Surveyor Manager |
| PLO | • Provisionary Accredited Subcontractors shall have a monthly or area specific service contract. This is to allow the company to end the contract of non-performing subcontractors. Performing subcontractors shall be rewarded with work continuity and accreditation by the PLO if their requirements are met. For Accredited Subcontractors, service agreement shall cover up to acceptance of the service/work. | Service Agreement |
| PLO, Quantity Surveyor Manager | • The PLO department shall be in-charge in accomplishing the service agreement including notarization (if required). The Quantity Surveyor Manager also assists the PLO department in making sure that the contract was signed by the subcontractor before his commencement of work. The Quantity Surveyor Group conducts regular inspection of all concerned project sites to ensure that the terms in the contract are being followed throughout the execution of work which includes the monitoring of needed materials and tools to complete the job. Note: All service agreement shall be accomplished prior to mobilization and/or start of work by the subcontractor. | Service Agreement, Subcontractor |
|  | 5.3. Subcontractor Billing |  |
| Subcontractor | • The subcontractor requests verbally to the Project Engineer for the billing of their accomplishment. All weekly billings and/or progress billings shall follow the terms indicated in the Service Agreement. For Specialty Works, billing documents shall be accomplished by them. Their billing shall only be entertained by the Project Engineering and Technical Team upon submission of their documents. In the case of Labor Only Subcontractors and Soil Haulers, billing documents shall be prepared by the Project Engineering and Technical Team. | Project Engineering Team & Technical Team |

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 6 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

|  | 5.3.1 Validation |  |
| --- | --- | --- |
|  | 5.3.1.1 Labor Only Subcontractor |  |
| Project Engineering and Technical Team | • The Project Engineering and Technical Team conducts a visual inspection and/or the necessary testing and commissioning of the accomplished work. If it passes all the requirements stipulated in the service agreement, the billing will commence. On the other hand, if it fails to comply, the subcontractor will make the necessary corrections or rectification until the work is accepted by the contractor. For Specialty Works Subcontractors, their billing shall only be entertained by the General Contractor upon submission of their documents. | Service Agreement Subcontractor |
| Project Engineering and Technical Team | If the work is accepted, the Project Engineering and Technical Team will prepare a working drawing of the work subjected for billing. | Working Drawing |
| Project Engineering and Technical Team or Subcontractor | • Perform actual measurement together with the subcontractor. Jot down measurements to the working drawings. Cut-off date for measurement will follow the conditions set forth in the service agreement. | Working Drawing |
| PLO | • Conduct verification of measurements and visual inspection of the areas subjected for billing by the subcontractor. In case of invalidation of measurements by the PLO, a joint measurement and inspection will be conducted to resolve the issue. | Working Drawings, Project Engineering and Technical Team, Subcontractor |
| Project Engineering and Technical Team | • Generated billing amount based on validated measurements will be verified and accepted by the subcontractor prior to documentation by the project engineer. | Subcontractor |

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 7 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

|  | 5.3.1.2 Specialty Work Subcontractor |  |
| --- | --- | --- |
| Project Engineering and Technical Team | • Validation of billing of Specialty Work Subcontractor shall be subjected for review and approval by the Project Manager and Operations Manager. The Project Engineering and Technical Team shall prepare an actual computation in comparison with the subcontractors’ data | Subcontractor Project Manager Operations Manager |
| Operations Manager/Project Manager | • A net difference of +-10% shall be accepted. In any case the computed accomplishment by the Project Engineering and Technical Team is less than 10% compared to subcontractors’ amount, the Project Manager or Operations Manager shall request further justification from the subcontractor for compromise. The final amount of progress billing shall be the amount agreed upon by both parties. Any changes to the billing documents shall be made by the subcontractor and will be re- submitted accordingly. | Subcontractor |
|  | 5.3.2. Documentation |  |
| Project Engineering and Technical Team | • Make an Acceptance Report. Simplify billing computation/calculation tables for easy checking by the finance department. Format of computation/calculation tables depends on the following: - Type of measurement (ex. linear meter, square meter, cubic meter, lump sum, kg etc.) - Type of work (ex. hauling, masonry works, fire pro, etc.) Note: For Specialty Works Subcontractor, attach comparison of accomplishment data as justification for their submitted billing. | Acceptance Report |

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 8 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

| Project Engineering and Technical Team | • Organize Working Drawings such that: o It will stand in correlation with the type of measurement performed and computation/calculation table presentation. o It marks the location of item to be billed with respect to the mother plan. It shows distinction of previously billed or unbilled items including similar scope of works performed by admin (for succeeding billing). | Working Drawing |
| --- | --- | --- |
| Project Engineering and Technical Team | • Make a sequential power point presentation of the accomplished work. Print at least one hard copy of the PowerPoint presentation. In case of outside project, email PowerPoint presentation to the PLO department. | PLO |
| Project Engineering and Technical Team | • Print two copies of subcontractor billing document. It is a compilation of the following: o Billing Acceptance Report o computation/calculation tables o working drawings o Note: For Specialty Works Subcontractor, attached submitted documents by them aside from the above documents. | Billing Acceptance |
| Project Engineering and Technical Team | • Rout the billing document for signatory of the subcontractor including the technical persons involved in the preparation and acceptance of the accomplished work. | Subcontractor Billing Subcontractor Project Manager Operations Manager Quantity Surveyor Manager |
|  | 5.3.3 Submission |  |
| Project Engineering and Technical Team, Quantity Surveyor Manager | • Subcontractor billing will be submitted to PLO based on the timeline or cut-off date stipulated in the service agreement. As part of the Quantity Surveyor Manager’s mandate to ensure that the terms in the contract is being followed, it is his task to follow-up the PLO department on the release subcontractors billing whenever it is due. | Service Agreement PLO |

|  | PROCEDURES MANUAL | Doc. Code : PM-OPN-06 |
| --- | --- | --- |
|  |  | Rev. No. : 1 |
|  |  | Eff. Date : |
|  |  | Page : 9 of 9 |
| TITLE: SUBCONTRACTOR MONITORING |  |  |

| PLO | • Conduct cross checking of the billing document. If the document submitted lacks supplemental attachments or table computations has typographical errors, the billing document will be returned to the project engineer for rectification and/or submission of additional attachment within the same day. | Subcontractor Billing |
| --- | --- | --- |
|  | 5.4 Evaluation Acceptance |  |
| Project Engineering and Technical Team | • The Project Engineering and Technical Team shall monitor the performance of each Subcontractor. Conduct performance evaluation of Subcontractors after every finished contract or as deemed necessary in any case of poor workmanship and violation of terms stipulated in the service agreement. | Subcontractor Performance Evaluation |
| Operations Manager | • The Operations Manager shall recommend non-renewal of contract for non-performing subcontractors. On the other hand, performing subcontractors shall be given continuity or additional work. | Performance Evaluation |
| Operations Manager/Project Manager | • Acceptance of Work done by Subcontractors shall be done by the Project Manager and/or Operations Manager. Issuance of Acceptance shall be upon request by the subcontractor on the condition that the work or portion of work is 100% accomplished. The date of issuance of the Certificate of Acceptance shall be the start of the warranty period. Note: Release of retention shall conform to the terms stipulated in the Service Agreement | Certificate of Acceptance |

6.0   APPENDICES

FM-OPN-06-01           Billing Acceptance Report

FM-OPN-06-02           Sub-Contractor Performance Evaluation Form

FM-OPN-06-03           Sub-Contractor Request Form